## Sheet1
| Project_Start: | 2020-12-01 |  | Project Name: xyz
| Display Week: | 1
[7 empty] | 2020-11-28 | [6 empty] | 2020-12-05 | [6 empty] | 2020-12-12 | [6 empty] | 2020-12-19 | [6 empty] | 2020-12-26 | [6 empty] | 2021-01-02 | [6 empty] | 2021-01-09 | [6 empty] | 2021-01-16 | [6 empty] | 2021-01-23 | [6 empty] | 2021-01-30 | [6 empty] | 2021-02-06 | [6 empty] | 2021-02-13 | [6 empty] | 2021-02-20 | [6 empty] | 2021-02-27 | [6 empty] | 2021-03-06
WBS | TASK | LED | START | END | DAY | PROGRESS | time axis 2020-11-28 to 2021-03-13
 | time axis 2020-11-28 to 2021-03-13
1 | Planning | Mr A
1.1 | Planning Initialtion |  | 2020-12-01 | 2020-12-04 | 3 | 80%
1.2 | Resoursce Planning |  | 2020-12-05 | 2020-12-11 | 6 | 80%
1.3 | Quality Planning |  | 2020-12-12 | 2020-12-17 | 5 | 90%
1.4 | Phase Review |  | 2020-12-18 | 2020-12-20 | 2 | 70%
2 | Analysis | Ms B
2.1 | Gathering Requirement |  | 2020-12-21 | 2020-12-24 | 3 | 70%
2.2 | Buliding trust & Rapport with user |  | 2020-12-25 | 2020-12-29 | 4 | 100%
2.3 | Documenting |  | 2020-12-30 | 2021-01-02 | 3 | 60%
2.4 | Develop Prelimin any data |  | 2021-01-03 | 2021-01-07 | 4 | 95%
3 | Design | Mr D
3.1 | Design 1 |  | 2021-01-08 | 2021-01-11 | 3 | 80%
3.2 | Design 2 |  | 2021-01-12 | 2021-01-16 | 4 | 78%
4 | Implementation | Mr E
4.1 | System construction |  | 2021-01-17 | 2021-01-20 | 3 | 65%
4.2 | Installation |  | 2021-01-21 | 2021-01-25 | 4 | 70%
4.3 | Support Plan System |  | 2021-01-26 | 2021-01-30 | 4 | 80%
5 | Completion | Ms C
5.1 | System Maintenance |  | 2021-01-31 | 2021-02-03 | 3 | 80%
5.2 | Testing |  | 2021-02-04 | 2021-02-08 | 4 | 70%
5.3 | Evaluation |  | 2021-02-09 | 2021-02-12 | 3 | 75%
5.4 | Deployment |  | 2021-02-13 | 2021-02-17 | 4 | 100%

## Holidays
Date |  | Holidays Name
2021-02-21 | Friday | Language Mothers Day
2021-03-17 | Tuesday | Mujib's Birthday & Children's Dayy
2020-03-25 | Wednesday | Genocide Remembrance Day
2021-03-26 | Thursday | Independence Day
2021-04-14 | Tuesday | Bengali New Year's Day
2021-05-01 | Friday | May Day
2020-05-07 | Thursday | Buddha's Birthday
2020-05-24 | Sunday | End of Ramadan (Eid al-Fitr)
2020-07-31 | Friday | End of Ramadan (Eid al-Fitr)
2020-08-11 | Tuesday | Krishna Janmashtami
2020-08-15 | Saturday | National Mourning Day
2020-08-29 | Saturday | Day of Ashura
2020-10-25 | Sunday | Durga Puja
2020-10-29 | Thursday | Birthday of Muhammad (Mawlid)
2020-11-21 | Saturday | Armed Forces Day
2020-12-14 | Monday | Martyred Intellectuals Day
2020-12-16 | Wednesday | Victory Day
2020-12-25 | Friday | Christmas Day
2021-03-11